## Sheet1
Feature	Index in GDD	Prototype Estimated Hours	Final Estimated Hours	Estimated Hours Remaining

Circuit board play space	1	1	3	3
each of the six sides is a pin (terminal) of the circuit	3	1	3	3
basic mode and expert mode	4	1	3	3
Options mode reverts to attract mode (title screen) when user is done setting options	31	1	3	3
Game text uses custom font(s)	40	1	3	3
Screen button for Play in attract and demo modes	59	1	3	3
Screen buttons for mute and unmute in pause mode	60	1	3	3
Local high scores can be cleared in options mode	65	1	3	3
Attract mode has Next buttons to immediately go to next screen (happens automatically after a time)	66	1	3	3
Attract mode has Demo button to immediately go to Demo mode (happens automatically after a time)	67	1	3	3
Demo mode has Done button to immediately return to attract mode title screen (happens automatically after a time)	68	1	3	3
Core screen space is ratio 9:16 (portrait mode) but playable on 3:4 and 10:16	69	1	3	3
Play space wide enough for 9 hex tiles, tall enough for 14 hex tiles	71	1	3	3
Hex tiles target resolution is 128x128	72	1	3	3
Button target resolution is 128x128	73	1	3	3
Target font size is 96 pt and larger	74	1	3	3
Background image resolution for screens is 1080x1920	75	1	3	3
Playspace area is hex-tiled honeycomb, 128x128 image tiles approx 1 per hexagon	76	1	3	3
A piece spawns at the top whenever the previous piece “lands”	11	2	6	6
If a spawned piece has no room to fall, the game is over	12	2	6	6
Sound on a piece landing and adding to a consistent circuit	13	2	6	6
Sound on an inconsistent circuit forming	14	2	6	6
Sound on a closed circuit disappearing	15	2	6	6
Sound at game over	16	2	6	6
Score is shown at the top of the screen	19	2	6	6
Game title on one screen of the attract mode	23	2	6	6
When player loses, game over mode appears till user is done, then attract mode, title screen resumes	34	2	6	6
More points-per-closed-circuit for higher tick rate and for expert mode	44	2	6	6
Scoring piece vanishes	53	2	6	6
hexagon-shaped circuit elements	2	3	9	9
elements fall until they land on another element or the bottom of the play space	5	3	9	9
elements can be shifted left or right as they fall	6	3	9	9
elements can be rotated in 60-degree increments as they fall	7	3	9	9
Elements, when landing, try to fit into the honeycomb efficiently	8	3	9	9
Inconsistent regions of elements are “dead” and are grayed out	9	3	9	9
Basic mode: pins determined to have a definite truth value get a color showing that value	17	3	9	9
Basic mode: conflicting pins of inconsistent circuits highlighted	18	3	9	9
Game description on one screen of the attract mode	24	3	9	9
Pause menu shows a pause screen	37	3	9	9
Screen button for Done in pause, options, and game over modes	58	3	9	9
High scores are persistent on architectures that support it	63	3	9	9
Target resolution is 1080x1920 but playable at lower and higher resolutions	70	3	9	9
Closed regions (consistent and having a unique solution on all exposed pins) disappear and add to the score	10	5	15	15
High scores are displayed on one screen of the attract mode	22	5	15	15
Attract mode (which cycles through its screens) to demo mode to attract mode cycles till user decides to play or set options	30	5	15	15
Game over mode gives score, and info if player made a high score	35	5	15	15
Options include sound volume, music volume, player name, basic or expert mode, tick rate	36	5	15	15
Support stand-alone, web, and mobile	45	5	15	15
Screen buttons for rotate left, rotate right, and pause in play mode	57	5	15	15
Screen controls for all the options in options mode	61	5	15	15
All controls and buttons have keyboard, mouse button, and/or gamepad shortcuts	62	5	15	15
Game modes: attract, play, demo, pause, set options, game over	20	8	24	24
High scores are maintained	21	8	24	24
Play mode goes to pause mode if selected by user	32	8	24	24
When pause mode is done, play mode resumes	33	8	24	24
Circuit look balanced between realistic and easy to visually parse	39	8	24	24
Logos and symbols on title screen in addition to title/author/etc	41	8	24	24
Support sites like itch.io and Windows Store	46	8	24	24
Animations to some of the pieces	47	8	24	24
Pieces have states: falling, settling, stable, scoring, dead	48	8	24	24
Falling piece becomes settling piece when it lands on another	49	8	24	24
Settling piece becomes stable when it integrates with the honeycomb	50	8	24	24
Stable piece becomes dead on becoming part of unsatisfiable circuit	51	8	24	24
Stable piece becomes scoring on becoming part of a closed circuit	52	8	24	24
Controllable by keyboard, gamepad, touch screen, and/or mouse	56	8	24	24
High scores are networked on architectures/venues that support it	64	8	24	24
Attract mode switches to demo mode, which reverts to attract mode when the demo AI player loses or after a fixed time	25	13	39	39
Music A during attract mode and during demo mode	26	13	39	39
Music B during pause mode and during options mode	27	13	39	39
Music C during play mode	28	13	39	39
Music D during game over mode	29	13	39	39
More than one play mode music, changes with progress	38	13	39	39
All game piece movement is in discrete steps at a definite (tuneable) tick rate	43	13	39	39
Stable piece or dead piece becomes falling piece if an adjacent piece below it vanishes	54	13	39	39
Dead pieces become stable pieces if they are no longer unsatisfiable	55	13	39	39
Well-designed borders/background for all modes and screens, balancing artistic with readability	42	21	63	63
	77		0	0
	78		0	0
	79		0	0
	80		0	0
	81		0	0
	82		0	0
	83		0	0
	84		0	0
	85		0	0
	86		0	0
	87		0	0
	88		0	0
	89		0	0
	90		0	0
	91		0	0
	92		0	0
	93		0	0
	94		0	0
	95		0	0
	96		0	0
	97		0	0
	98		0	0
	99		0	0
	100		0	0
Total hours	101	382	1146	1146
	102
	103
	104
	105
	106
	107
	108
	109
	110
	111
	112
	113
	114
	115
	116
	117
	118
	119
	120
	121
	122
	123
	124
	125
	126
	127
	128
	129
	130
	131
	132
	133
	134
	135
	136
	137
	138
	139
	140
	141
	142
	143
	144
	145
	146
	147
	148
	149
	150
	151
	152
	153
	154
	155
	156
	157
	158
	159
	160
	161
	162
	163
	164
	165
	166
	167
	168
	169
	170
	171
	172
	173
	174
	175
	176
	177
	178
	179
	180
	181
	182
	183
	184
	185
	186
	187
	188
	189
	190
	191
	192
	193
	194
	195
	196
	197
	198
	199